## Working route
Blackboard Group No 1 Class CPR101NBB | Project Planning |  |  |  |  | Version 1 |  |  |  |  | Version 2 (optional) |  |  |  |  | Version 3 (option) |  |  |  |  | Last Chance Submission
SMART goals ==> | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP
reference and relative due dates |  | Update E3 to your PM class date | =====> | 2023-07-29 | Friday Jul.28 |  |  | PM class date plus | 9 | days |  |  | PM class date plus | 14 | days |  |  | PM class date plus | -226 | days | Latest possible submission is last day of classes; late penalties apply at 20% per day after your Version 3 due date: | 2022-12-15
Each Team member | Your Project Mgmt notes on what each Process Group means to you when doing this project. | Share with team by uploading PM-Notes-myName.docx to Bb ## team channel's Files |  | Sunday Jul.30 | DONE | completes their module. For specific tasks, see Final Project Overview and Project Milestones and Details | see Programming Comments and Programming Test Cases docs for acceptance criteria. See Project Overview - Appendix B for deliverables |  | see Project Milestones and Details | DONE | completes their module. For specific tasks, see Final Project Overview and Project Milestones and Details | see Programming Comments and Programming Test Cases docs for acceptance criteria. See Project Overview - Appendix B for deliverables |  | see Project Milestones and Details |  | completes their module. For specific tasks, see Final Project Overview and Project Milestones and Details | see Programming Comments and Programming Test Cases docs for acceptance criteria. See Project Overview - Appendix B for deliverables |  | see Project Milestones and Details
Team Meeting Agenda ==> | create MS Teams Private Channel; for Version 1, create plan with SMART goals and assign tasks | detailed tasks assigned to Team members with est. hrs., agreed upon delivery date to Teams, updated Status | 1.5 | Monday Jul.31 | DONE | review progress, refine Plan, update DONE items with actual hours, refine estimates and delivery date/time | In MS Team Channel, select any file you would like reviewed and send a message @instructor to comment on that file. |  | Friday Aug.4 | DONE | Team decision whether to do this version. If so, members plan to complete V2 of their module. | detailed tasks assigned to Team members with est. hrs., agreed upon delivery date/time to Teams, updated Status |  | Wednesday Dec.14 | TO DO | Team decision whether to do this version. If so, members plan to complete V3 of their module. | detailed tasks assigned to Team members with est. hrs., agreed upon delivery date/time to Teams, updated Status |  | Monday Dec.12 | TO DO | Submit final version of artefacts from Teams to Blackboard in a .ZIP archive. Backup Team's files. | updated all DONE items with actual hours. |  | Monday Dec.12 | TO DO
| request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." |  | Tuesday Aug.1 |  | request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." |  | Friday Aug.4 | DONE | request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." |  | Wednesday Aug.9 | TO DO | request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." |  | Monday Dec.12 | TO DO
[Srijan Sehgal] Fundamentals | I have been assigned the module of fundamentals.I will make sure my tasks are completed on time and also review each other's PM notes on process Teams. Agree on how project will be done. | We reached an agreement of the due date of the first versionof this project and made sure everyone knows their tasks and responsabilities. We also dediced to have two leaders to split the responsibilities of the leader, for instance, checking other member's work, converting and uploading the project to GitHub. Also, we agreed on asking the professor to review our planning in class. | Realistic hours: 1 hour, Actual hours: 45 mins | Monday Jul.31 | DONE | My responsibility for version 1 is commenting the header and source file of fundamentals module. After commenting them, they are to be compiled and the test cases both positive and negative are to be recorded on an excel file. moreover, the inputa and outputs on the console are to be copy pasted in a text file for completion of the task. | The measure of our deliverable involves a few key aspects. Firstly, while commenting the source code we have to make sure that the comments explain what the step does not how. secondly the code is easy to understand by others. After commenting the files, the second thing c=that comes is running the code and recording the test cases. Test cases should include nominal and edge cases as well so that it is verified how the code works under different conditions. After the testing is done we have to record the test cases in an excel file and paste the results of console in a text file. We have talked about all these steps and thus agree on our deliverable criteria. | 1 hour 30 minutes | Saturday Aug.5 | DONE | My task for version 2 included working with the fundamentals module. Firstly, commenting out the code for version 2 to make it understandable for the readers. In addition to version 1, version 2 required working with git to present a log text of both the versions. This version also included performing positive and negative test cases and recording them on an excel file as well as pasting the console output on a text file for the project submission. | The measure of our deliverable involves a few key aspects. Firstly, while commenting the source code we have to make sure that the comments explain what the step does not how. secondly the code is easy to understand by others. After commenting the files, the second thing c=that comes is running the code and recording the test cases. Test cases should include nominal and edge cases as well so that it is verified how the code works under different conditions. After the testing is done we have to record the test cases in an excel file and paste the results of console in a text file. We have talked about all these steps and thus agree on our deliverable criteria. | 2 hours | Thursday Aug.10 | DONE | REPLACE THIS with your action items and work breakdown structure for this Version |  |  | Tuesday Dec.13 |  |  |  |  | Tuesday Dec.13
[Misato Yoshimoto] Manipulations | I have been assigned the module of manipulations.I will make sure my tasks are completed on time and also review each other's PM notes on process Teams. Agree on how project will be done. I also check the Version 1 information and prepare for the next activity. | We reached an agreement of the due date of the first versionof this project and made sure everyone knows their tasks and responsabilities. We also dediced to have two leaders to split the responsibilities of the leader, for instance, checking other member's work, converting and uploading the project to GitHub. Also, we agreed on asking the professor to review our planning in class. | Realistic hours: 1 hour, Actual hours: 45 mins | Monday Jul.31 | DONE | My specific task in version 1 is to create a header and C file dedicated to code manipulation with comprehensive comments. Additionally, I am responsible for executing the code and conducting both positive and negative test cases. The results of these test cases will be carefully documented in an Excel. Additionally, all on-screen results will be copied to a TXT file for record keeping. | The measure of our deliverable involves a few key aspects. First, when commenting C-files for code manipulation, I make sure that the code is properly commented so that it is easy for others to understand and work with. Second, the testing phase plays an important role in the measurement. By including both positive and negative scenarios, a comprehensive assessment of the code's performance under different conditions can be made. The results of these tests can be documented on an Excel sheet so that the team is aware of the code's functionality and potential problems. We've talked about the content we need in the header and C files, the types of tests we should run, and how we'll organize the Excel sheet to record our findings. Thus, we are all agreed on our deliverable criteria． | 1 hour and 30 mins 1 hour and 30 mins | Saturday Aug.5 | DONE | My specific task in version 2 is to work on a C file dedicated to code manipulation, including comprehensive comments. Version 2 requires, specifically, the use of git to manage our codebaseand and provide log data for version 1 and version 2. It is also my job to run version 2 of the code operation and implement both positive and negative test cases. The results of the test cases will be recorded in Excel and TXT files. | The measure of our deliverable involves a few key aspects. First, when commenting C-files for code manipulation, I make sure that the code is properly commented so that it is easy for others to understand and work with. Second, the testing phase plays an important role in the measurement. By including both positive and negative scenarios, a comprehensive assessment of the code's performance under different conditions can be made. The results of these tests can be documented on an Excel sheet so that the team is aware of the code's functionality and potential problems. We've talked about the content we need in the header and C files, the types of tests we should run, and how we'll organize the Excel sheet to record our findings. Thus, we are all agreed on our deliverable criteria． | 2 hours | Thursday Aug.10 | DONE | REPLACE THIS with your action items and work breakdown structure for this Version |  |  | Tuesday Dec.13 |  |  |  |  | Tuesday Dec.13
[Ashwin B N] Tokenizing | I have been assigned the module of tokenizing. I will make sure my tasks are completed on time and also review each other's PM notes on process Teams. Agree on how project will be done. | We reached an agreement of the due date of the first versionof this project and made sure everyone knows their tasks and responsabilities. We also dediced to have two leaders to split the responsibilities of the leader, for instance, checking other member's work, converting and uploading the project to GitHub. Also, we agreed on asking the professor to review our planning in class. | Realistic hours: 1 hour, Actual hours: 45 mins | Monday Jul.31 | DONE | In version 1 of my task, I'm working on making a special header and C file that helps break words into smaller parts. I'm adding detailed explanations to the code to help others understand it better. Also, I'm in charge of running the code and trying different situations where things could go well or not so well. The outcomes of these tests will be written down carefully in an Excel sheet. And I'll also save all the things that show up on the screen in a text file so we can keep track of everything. | Our way of measuring our work involves a few important things. First, when I write explanations in C program files to split words, I make sure to write them in a way that's easy for others to understand and use. Second, testing is really important. We try out different situations, both good and bad, to see how well the code works. We write down what happens during these tests in an Excel file so our team knows how the code works and if there are any issues. We've also discussed what information should be at the beginning of our program files, the types of tests we should do, and how we'll organize the Excel file to keep track of our findings. So, we all agree on how we'll decide if our work is good enough. | 2 hours | Saturday Aug.5 | DONE | In relation to the second phase of the tokenizing.c development, I assume the responsibility of advancing the codebase, meticulously refining and expanding its functionality. My tasks encompass not only the coding aspect but also extend to the realm of quality assurance, where I ensure the thorough testing of the developed code. This involves the meticulous crafting and execution of comprehensive test scenarios to validate the accuracy and robustness of the tokenization process. Additionally, I will diligently capture and document observations, insights, and potential optimizations throughout the development journey, ensuring that a detailed record of progress is maintained for future reference and continuous improvement. | The measurement of delivery and the establishment of delivery criteria are essential aspects of project management that contribute to the successful execution of tasks and the achievement of project goals. In our project group, it is imperative to have clear and agreed-upon criteria for measuring deliverables to ensure a shared understanding of expectations and outcomes. This collaborative approach helps avoid misunderstandings and aligns all team members toward a common understanding of what constitutes successful delivery. | 1.5 hours | Thursday Aug.10 | DONE | REPLACE THIS with your action items and work breakdown structure for this Version |  |  | Tuesday Dec.13 |  |  |  |  | Tuesday Dec.13
[Maryam Setayeshnia & Vinicius Souza da Silva] Conversions Team Leader | team leader is responsible for module D along with synchronizing development and integrating modules into the main application. | We reached an agreement of the due date of the first versionof this project and made sure everyone knows their tasks and responsabilities. We also dediced to have two leaders to split the responsibilities of the leader, for instance, checking other member's work, converting and uploading the project to GitHub. Also, we agreed on asking the professor to review our planning in class. | relaistic planned hours : 45 minutes , Actucal hours: 1 | Tuesday Aug.1 | DONE | In version 1 , the leaders'stask was commenting and testing the converting module. This module takes an integer string and cnverts it into an actual integer. We commented each statement of this program in an understandable and readable way. We did testing the edge-cases and transferred those parts to the an excel shhet. Also, we had to combine all codes after reading them carfully in one folder and create a main.c part and compile that program to see if the program works properly. Additionally, we transfered thet test-casese excel sheet of each programmer to one file and put it in the zip folder. | C-file comments are crucial for improving the readability and maintainability of the code. My teammates uploaded their work to respective modules, which I carefully studied to see if my team's comments made the software easier to read. Additionally, the tested edge-cases give a clearer picture of how the program behaves with various outputs or what needs to be taken into account. The testing phase is an important part of the development process, and by taking into account both positive and negative scenarios, you can make sure that the code is able to handle a range of inputs and edge cases. This thorough evaluation makes that the code performs well in a variety of scenarios and helps to identify any potential problems. Documenting the test results on an Excel sheet is an effective way to keep track of the code's functionality and identify any problems that need to be addressed. This documentation also fosters transparency within the team, allowing everyone to be aware of the code's status and progress. | 2 hours | Sunday Aug.6 | DONE | My responsibilities are, the making of GitHub repository and Git configurations for both Version 1 and Version 2 of the project. Within this role, I will be engaged in the process of uploading essential test suites, integrating a comprehensive gitlog text file to document the development timeline, performing compilation procedures, and diligently recording noteworthy observations and insights as part of the project's evolution. | The measure of success for the deliverable is determined by the execution and completion of the outlined tasks as described in the provided text. The accomplishment of setting up GitHub repositories, configuring Git environments for both Version 1 and Version 2 of the project, uploading the requisite test suites, integrating the gitlog text file to chronicle the development process, conducting compilation processes, and maintaining comprehensive notes to track progress all collectively constitute the delivery criteria. This criteria is established and agreed upon within the project to ensure that the specified tasks are completed to meet the project's objectives and milestones. | 1:30 | Friday Aug.11 |  | REPLACE THIS with your action items and work breakdown structure for this Version |  |  | Wednesday Dec.14 |  |  |  |  | Wednesday Dec.14
|  |  |  | milestone upload to Blackboard |  |  |  |  | milestone upload to Blackboard |  |  |  |  | milestone upload to Blackboard |  |  |  |  | DUE DATE upload to Blackboard |  |  |  |  | ABSOLUTE DEADLINE
[6 empty] | "Work on [module name]" is not specific. There are tasks with a critical path. WBS? Filenames to be uploaded to your team's Files area. | What is the team's criteria for acceptance of development (files on developer's PC) when promoted to integration (Files in team's channel) What file names? What is definition of done / good enough? Who decides that? Project Overview and Programming Comments¦Testing docs have this information to be quoted or referenced. Requests for professor's review come after the team has accepted the work. | [11 empty] | submissions after this date subject to extra time charge of 20% per day |  |  |  |  | no submissions accepted after this date
Note on A1: Update ?? to your Blackboard group number and XYY to your CPR101XYY class code. Then press TAB to next set up item in E3.
Note on A2: Use SMART goals to achieve the Triple Constraint of Cost/Resource vs Time/Schedule vs Scope/Quality.
Note on B2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on C2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on D2: How many hours will the task take?
Note on E2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on F2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on G2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on H2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on I2: How many hours will the task take?
Note on J2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on K2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on L2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on M2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on N2: How many hours will the task take?
Note on O2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on P2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on Q2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on R2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on S2: How many hours will the task take?
Note on T2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on U2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on V2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on W2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on X2: How many hours will the task take?
Note on Y2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on Z2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on E3: Change this to the date of your Project Management class and the worksheet will calculate all milestone dates.